## Plan
Task | Planned Time(hr) | Actual Time(hr)
Planning & Base Project | 0.5 | 0.5
Multiplayer Movement | 2 | 2.5
Camera | 0.5 | 0.3
Floor Creation | 2 | 2
Bomb placement | 1.5 | 1
Bomb Collision Check | 1.5 | 2 | Legends
Destruction of Bricks | 1 | 0.5 |  | Future Tasks
Pickups(Bombs,Speed) | 2 | 1.5
Pickups(Detonator) | 1 | 0.5
HUD | 1
UI | 1
Save Data | 1
AI(optional) | 2
Bomb & Brick FX(Optional) | 2
Sounds(optional) | 1
Total | 20 | 10.8