## Plan
Task | Planned Time(hr) | Actual Time(hr)
Planning & Base Project | 0.5 | 0.5
Multiplayer Movement | 2 | 2.5
Camera | 0.5 | 0.3
Floor Creation | 2 | 2
Bomb placement | 1.5
Bomb Collision Check | 1.5
Destruction of Bricks | 1
Pickups(Bombs,Speed) | 2
Pickups(Detonator) | 1
HUD | 1
UI | 1
Save Data | 1
AI(optional) | 2
Total | 17 | 5.3