## Plan
Task | Planned Time(hr) | Actual Time(hr) | Remarks
Planning & Base Project | 0.5 | 0.5
Multiplayer Movement | 2 | 2.5
Camera | 0.5 | 0.3
Floor Creation | 2 | 2 |  | Future Task
Bomb placement | 1.5 | 1 |  | AI which works as Player
Bomb Collision Check | 1.5 | 2 |  | Neutral characters
Destruction of Bricks | 1 | 0.5 |  | Effects
Pickups(Bombs,Speed) | 2 | 1.5
Pickups(Detonator) | 1 | 0.5
HUD | 1 | 0.5
UI | 1 | 1
Save Data | 1 | 1.5
Sounds |  | 0.5
Testing |  | 0.5
Total | 15 | 14.8